## Feuil1
Planning for Soregies Agreement
# | validation | November
X | signature | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1- Eon Permits
Validation comité risque EFR (IPa) | bar: November 6
Validation comité risque EEA (PUl) | bar: November 16 to November 17; November 19
2.- Soregies permits (J Delagrandanne)
Bank pool validation | bar: November 20
Soregies Management Board validation | bar: November 13
3.- Main Contract Amendment (P Gouillart)
Amendment First Draft (PGo) | bar: November 2 to November 5
Discussions with Soregies (AHa -PGo) | bar: November 18 to November 20
legal validation (PGa) | bar: November 16 to November 19
Final Amendment (PGo) | bar: November 20
Amendment validation (EFR management board AHa) | bar: November 23
Signature (PGo) | bar: November 26
4.- Call Option (JC Bissié)
Contract definition (JCB) | bar: November 2 to November 6; November 9 to November 10; November 12
Discusions with Soregies (JCB) | bar: November 16 to November 18
Management board validation (AHa) | bar: November 19 to November 20; November 23
Legal Fine tuning (PGa) | bar: November 16 to November 20
Call option signature (PGo) | bar: November 26
5- Back to Back Call Option Tender (JC Bissié)
Term sheet definition (JCB) | bar: November 2 to November 6; November 9 to November 10
Process definition (JCB/PGo) | bar: November 16 to November 18
Contreparties selection (PMu/IPa) | bar: November 3 to November 6; November 9 to November 10; November 12 to November 13; November 16 to November 17
Eon permit (AHa) | bar: November 18 to November 20
Tender launching (JHi/MPo) | bar: November 17
First non bidding offer | bar: November 24
Bidding offer | bar: November 25
B t B Call option confirmation | bar: November 26
A Ha | Antonio Haya
P Mu | Paco Munoz
P Ul | Philipp Ulbrich
P Ga | Pauline Gaget
JCB | Jean Charles Bissié
P Go | Philippe Gouillart
I Pa | Isabelle Passicos
J Hi | Jean Hilbrunner
M Po | Matthieu Pottlitzer