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	Board Decision/Information

	on:
	04/05/2009

	
	


	Author:
	J-F Perret

	Recipients:
	Luc Poyer / Robert Hienz / Antonio Haya

	Point in the agenda:
	N°6

	Subject:
	BIOMASS LUCY

	

	Purpose:

	Biomass CHP plant project in the frame of  the national tender CRE3.

The Project is located on our site of Lucy with, as heating power consumer, the heating network of the municipality of Montceau operated by SOCCRAM (concession ending in 2019).

The pre feasability report shows the project could fit with the CRE 3 tender criteria.

Main characteristics of the Project:

· Boiler gross Power : 
25 MW

· Puissance électrique alternateur : 
4,5 MWe

· Investment (2010/2011): 
25 M€

· Biomass:
100.000 t/a

A 10% IRR could be reached with an electricity sales price of 160 €/MWh, a heating power price of 30 €/MWh and a purchasing price of the wood chips at 50 €/tonne.



	IV.



	Decision/Information:

	Submittal of an offer on 13/07/2009; first deadline being the remittance of a biomass supply scheme to the local authorities (prefet) not later than the 29/05/09.

Such a study should be ordered to the Forestry associations (ONF/GCF) not later than 18/05/2009 to be delivered on time. Decision on budget approval of 18K€.
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